## Sheet1
#iGiveCatholic Coordinator
Scope of Work template |  | Hourly Rate | 20
Month | Duties | Estimated Hours | Subtotal
January |  | 3 | 60
| Plan & lead debrief meeting for #iGiveCatholic program evaluation | 3 | 60
0
February |  | 8 | 160
| View training videos and familiarize with program (1st year only) | 5 | 100
| Prepare and participate in #iGC Partner Gathering | 3 | 60
0
March |  | 6 | 120
| Prospect & solicit potential sponsors | 5 | 100
| Send emails to elligible ministries announcing #iGC and/or inviting to Top Ten Webinar | 1 | 20
0
0
April |  | 10 | 200
| Continue to solicit & steward sponsors | 5 | 100
| Attend virtual Top Ten Webinar | 1 | 20
| Plan and host informational meeting for inquiring ministries | 4 | 80
0
0
May |  | 6 | 120
| Attend Onboarding Webinar (1st year only) | 1 | 20
| Continue to solicit & steward sponsors | 5 | 100
0
0
June |  | 5 | 100
| Attend Office Hours Kick-Off | 1 | 20
| Continue to solicit & steward sponsors | 2 | 40
| Plan diocesan prizes and match opportunities | 2 | 40
0
July |  | 8 | 160
| Attend Office Hours | 1 | 20
| Respond to ministry questions | 5 | 100
| Update copy on platform (landing pages,sponsors, prizes, etc.) | 2 | 40
0
0
August |  | 22 | 440
| Attend Office Hours | 1 | 20
| Register and set-up diocesan campaign profiles | 5 | 100
| Respond to ministry questions | 5 | 100
| Coordinate communications re: organization registration | 5 | 100
| Approve organization registrations | 3 | 60
| Attend Get Ready Webinar | 1 | 20
| Coordinate OSV envelope order and distribution | 2 | 40
0
0
September |  | 23 | 460
| Attend Office Hours | 1 | 20
| Respond to ministry questions | 10 | 200
| Distribute weekly "Just One Thing" emails | 4 | 80
| Plan and host organization training session (in-person or virtual) | 5 | 100
| Approve organization registrations | 3 | 60
0
0
October |  | 18 | 360
| Attend Office Hours | 1 | 20
| Respond to ministry questions | 10 | 200
| Distribute weekly "Just One Thing" emails | 4 | 80
| Approve organization registrations | 3 | 60
0
0
November |  | 27 | 540
| Attend Office Hours | 1 | 20
| Respond to ministry questions | 8 | 160
| Distribute weekly "Just One Thing" emails | 4 | 80
| Attend Final Steps Webinar | 1 | 20
| Troubleshoot potential issues before donations start | 3 | 60
| Coordinate communications re: Advanced Giving & Giving Day | 3 | 60
| Create and distribute communications re: diocesan campaigns | 4 | 80
| Plan and host in-person event (advanced giving happy hour, blood or goods drive, yard-sign giveaway, giving day prayer breakfast, etc.) | 3 | 60
0
0
December |  | 14 | 280
| Respond to ministry questions | 3 | 60
| Create and distribute communications re: diocesan campaigns | 1 | 20
| Determine and award prizes | 1 | 20
| Download diocesan reports & determine campaign results | 3 | 60
| Coordinate communications re: results (press release) | 3 | 60
| Calculate fiscal sponsor distribution (with finance) | 2 | 40
| Thank and steward sponsors | 1 | 20
0
0
CAMPAIGN TOTAL |  | 150 | 3000